## Summary
Summary
MileStone | Delivery Details | Planned |  | Actuals |  | Test Scenario Count |  | Acceptance Status ( by DRSYS QA)
|  | Start Date | End Date | Start date | End Date | Planned | Actual
Milestone 1 | AMC - Stage 2 - Part 1 | 2014-09-12 | 2014-10-23 | 2014-09-12 | 2014-10-20 | 45 | 45
Milestone 2 | AMC - Stage 2 - Part 2 | 2014-10-24 | 2014-11-24 | 2014-10-21 | 2014-11-24 | 48 | 48

## MileStone1
Milestone 1 Delivery Details
QC Test Scenario ID | Section | Title | Delivered | Actual Milestone | Acceptance Status ( by DRSYS QA) | Accepted By | Accepted Date
221 | CPOE - Medication Orders | CPOE for Medication Orders measure does not take into account deleted medications. | Yes | Milestone1
5793 | CPOE - Medication Orders | CPOE Medications does not take into account Inactive Medications on Health Status tab | Yes | Milestone1
5794 | CPOE - Medication Orders | CPOE for Medication Orders measure does not take into account cancelled medication orders. | Yes | Milestone1
703 | CPOE - Medication Orders | Denominator for CPOE for medication orders Stage 2 AMC measure. | Yes | Milestone1
704 | CPOE - Medication Orders | Numerator for CPOE for medication orders Stage 2 AMC measure. | Yes | Milestone1
5805 | CPOE - Medication Orders | Help text and Requirement for CPOE for Medications Orders. | Yes | Milestone1
223 | CPOE - Laboratory Orders | CPOE for laboratory orders measure does not take into account cancelled laboratory orders. | Yes | Milestone1
4846 | CPOE - Laboratory Orders | CPOE for laboratory orders Stage 2 does not consider orders placed outside reporting period. | Yes | Milestone1
707 | CPOE - Laboratory Orders | Denominator for CPOE for laboratory orders Stage 2 AMC measure. | Yes | Milestone1
5804 | CPOE - Laboratory Orders | Help text and Requirement for Stage 2 CPOE for laboratory orders. | Yes | Milestone1
708 | CPOE - Laboratory Orders | Numerator for CPOE for laboratory orders Stage 2 AMC measure. | Yes | Milestone1
222 | CPOE - Radiology Orders | CPOE for radiology orders measure does not take into account cancelled radiology orders. | Yes | Milestone1
4847 | CPOE - Radiology Orders | CPOE for radiology orders Stage 2 measure does not take into account orders outside RP. | Yes | Milestone1
705 | CPOE - Radiology Orders | Denominator for CPOE for radiology orders Stage 2 AMC measure. | Yes | Milestone1
5806 | CPOE - Radiology Orders | Help text and Requirement column for Stage 2 CPOE for Radiology Orders. | Yes | Milestone1
706 | CPOE - Radiology Orders | Numerator for CPOE for radiology orders Stage 2 AMC measure. | Yes | Milestone1
4789 | Demographics | Demographics Stage 2 AMC measure. (Negative Scenarios) | Yes | Milestone1
4788 | Demographics | Demographics Stage 2 AMC measure. (Positive Scenario) | Yes | Milestone1
4787 | Demographics | Demographics Stage 2 AMC measure does not take into account patients with inactive visits. | Yes | Milestone1
4786 | Demographics | Demographics Stage 2 AMC measure does not take into account Inpatients. | Yes | Milestone1
4785 | Demographics | Demographics Stage 2 AMC measure does not take into account non face-to-face patients. | Yes | Milestone1
4784 | Demographics | Demographics Stage 2 AMC measure does not take into account patients seen outside reporting period. | Yes | Milestone1
192 | Demographics | Help text and Requirement for Stage 2 Demographics AMC measure. | Yes | Milestone1
4793 | Record Electronic Notes | Record Electronic Notes Stage 2 AMC measure does not account patients with inactive visit. | Yes | Milestone1
4792 | Record Electronic Notes | Record Electronic Notes Stage 2 AMC measure does not account Inpatients. | Yes | Milestone1
4791 | Record Electronic Notes | Record Electronic Notes Stage 2 AMC measure does not account non face-to-face patients. | Yes | Milestone1
4790 | Record Electronic Notes | Record Electronic Notes Stage 2 AMC measure does not account patients seen outside reporting period. | Yes | Milestone1
678 | Record Electronic Notes | Record Electronic Notes stage 2 AMC measure. | Yes | Milestone1
676 | Record Electronic Notes | Help text and Requirement column value for Record Electronic Notes stage 2 AMC measure. | Yes | Milestone1
709 | Generate and transmit eRx | Denominator for Generate and transmit eRx stage 2 AMC measure. | Yes | Milestone1
5811 | Generate and transmit eRx | Generate and transmit eRx does not take into account orders created outside reporting period. | Yes | Milestone1
25 | Generate and transmit eRx | Help text for e-Prescribing measure and Threshold measure in AMC stage 2 report. | Yes | Milestone1
710 | Generate and transmit eRx | Numerator for Generate and transmit eRx stage 2 AMC measure. | Yes | Milestone1
5812 | Generate and transmit eRx | Stage 2 Generate and transmit eRx does not take into account orders for controlled substances. | Yes | Milestone1
4796 | Family Health History | Family Health History does not account Inpatients. | Yes | Milestone1
4797 | Family Health History | Family Health History does not account patients with inactive status. | Yes | Milestone1
4794 | Family Health History | Family Health History does not account for patients seen outside reporting period. | Yes | Milestone1
4795 | Family Health History | Family Health History does not account non face-to-face patients. | Yes | Milestone1
402 | Family Health History | Family Health History stage 2 measure - Coded Family History | Yes | Milestone1
5754 | Family Health History | Family Health History stage 2 measure - More than 1 visit | Yes | Milestone1
5752 | Family Health History | Family Health History stage 2 measure - None Known | Yes | Milestone1
5753 | Family Health History | Family Health History stage 2 measure - Uncoded Family History | Yes | Milestone1
5755 | Family Health History | Family History Stage 2 does not take into account deleted Family History. | Yes | Milestone1
2184 | Family Health History | Family History Stage 2 does not take into account Inactive Family History. | Yes | Milestone1
396 | Family Health History | Help text and Requirement for Family Health History AMC stage 2 measure. | Yes | Milestone1

## MileStone2
Milestone 2 Delivery Details
QC Test Scenario ID | Section | Title | Delivered | Actual Milestone | Acceptance Status ( by DRSYS QA) | Accepted By | Accepted Date | Comments
567 | Generate Patient List | Help text and Requirement for generate Patient List AMC stage 2 measure | Yes | Milestone2
598 | Generate Patient List | Verification of Generate Patient List stage 2 AMC measure | Yes | Milestone2
669 | Patient Education | Help text and Requirement for Patient Education AMC stage 2 measure | Yes | Milestone2
6243 | Patient Education | Patient Education Material for patients with office visits within reporting period | Yes | Milestone2
6244 | Patient Education | Patient Education Material for patients with no office visits within reporting period | Yes | Milestone2
6245 | Patient Education | Patient Education does not consider period.patients seen outside reporting | Yes | Milestone2
6246 | Patient Education | Patient Education does not consider patients with non face-to-face visits | Yes | Milestone2
6247 | Patient Education | Patient Education does not consider patients with inpatient exams | Yes | Milestone2
6248 | Patient Education | Patient Education does not consider patients with inactive exams | Yes | Milestone2
666 | Preventive Care | Help text and Requirement column value for Preventive Care stage 2 AMC measure | Yes | Milestone2
668 | Preventive Care | Preventive Care stage 2 AMC measure takes into account the number of patients who have had 2 or more office visits and who were sent a reminder per patient preference | Yes | Milestone2
3229 | Preventive Care | Send button for Preventive Care AMC measure does not display when current date is not within reporting period | Yes | Milestone2
6627 | Preventive Care | Preventive Care does take into account patients seen outside reporting period | Yes | Milestone2
6628 | Preventive Care | Preventive Care does take into account for non face-to-face patients | Yes | Milestone2
6629 | Preventive Care | Preventive Care does not account Inpatients visits seen within reporting period | Yes | Milestone2
6630 | Preventive Care | Preventive Care does not take into account for patients with inactive visit | Yes | Milestone2
6631 | Preventive Care | Preventive Care does not account for patients who donot want receive reminders | Yes | Milestone2
6632 | Preventive Care | Preventive Care does not account patients with only 1 visits within 24 months prior to RP | Yes | Milestone2
61 | Smoking Status | Help text and threshold measure for smoking status measure on AMC stage 2 report | Yes | Milestone2
249 | Smoking Status | Verify Smoking Status stage 2 AMC measure | Yes | Milestone2
4798 | Smoking Status | Smoking Status Stage 2 AMC measure does not account for patients seen outside reporting period | Yes | Milestone2
4799 | Smoking Status | Smoking Status Stage 2 AMC measure does not take into account non face-to-face patients | Yes | Milestone2
4800 | Smoking Status | Smoking Status Stage 2 AMC measure does not take into account Inpatients | Yes | Milestone2
4801 | Smoking Status | Smoking Status Stage 2 AMC measure does not take into account patients with inactive visits | Yes | Milestone2
4802 | Smoking Status | Smoking status does not account for patients less than 13 years of age | Yes | Milestone2
6242 | Lab Results | Help text and Requirement for Stage 2 Incorporate Clinical Lab Results AMC measure | Yes | Milestone2
6227 | Lab Results | Stage 2 Incorporated Clinical Lab Results takes into account manually entered numeric results | Yes | Milestone2
6228 | Lab Results | Stage 2 Lab Results takes into account manually entered positive lab results | Yes | Milestone2
6229 | Lab Results | Stage 2 Lab Results takes into account manually entered negative lab results | Yes | Milestone2
6230 | Lab Results | Stage 2 Lab Results does not take into account results which are not positive, negative or numeric | Yes | Milestone2
6231 | Lab Results | Stage 2 Lab Results does not take into account manual results added outside reporting period | Yes | Milestone2
6232 | Lab Results | Stage 2 Lab Results does not take into account orders with cancelled status | Yes | Milestone2
6233 | Lab Results | Stage 2 Lab Results does not take into account lab results with inactive status | Yes | Milestone2
6234 | Lab Results | Stage 2 Lab Results does not take into account lab results deleted from system | Yes | Milestone2
6235 | Lab Results | Stage 2 Lab Results for multiple manually entered lab orders and lab results within reporting period | Yes | Milestone2
6549 | Lab Results | Stage 2 Lab results does not take into account uncoded (save as typed) lab results | Yes | Milestone2
717 | Med Reconciliation | Help text and threshold for Medication Reconciliation Stage 2 AMC measure. | Yes | Milestone2
3398 | Med Reconciliation | Stage 2 Med Reconciliation does not take into account patients seen by EP outside reporting period. | Yes | Milestone2
5511 | Med Reconciliation | Stage 2 Med Reconciliation does not take into account non Face to Face patients. | Yes | Milestone2
5512 | Med Reconciliation | Stage 2 Med Reconciliation does not take into account Inpatients seen by EP during reporting period. | Yes | Milestone2
5513 | Med Reconciliation | Stage 2 Med Reconciliation does not take into account patients with inactive visit during RP | Yes | Milestone2
5514 | Med Reconciliation | Stage 2 Med Reconciliation with first time visit and reconciliation by adding medication. | Yes | Milestone2
5515 | Med Reconciliation | Stage 2 Med Reconciliation with first time visit and reconciliation clicking None Known. | Yes | Milestone2
5516 | Med Reconciliation | Stage 2 Med Reconciliation with not first time visit with EP and TOC. | Yes | Milestone2
6563 | Med Reconciliation | Stage 2 Medication Reconciliation delete scenario - 1 | Yes | Milestone2
6564 | Med Reconciliation | Stage 2 Medication Reconciliation delete scenario - 2 | Yes | Milestone2
6565 | Med Reconciliation | Stage 2 Medication Reconciliation delete scenario - 3 | Yes | Milestone2
6566 | Med Reconciliation | Stage 2 Medication Reconciliation delete scenarios - 4 | Yes | Milestone2

## Script Review
Test Scripts Review Status
Folder | Script Name | Reviewed ? | Latest Reviewed Date | Script Update Date
\config | config.yml | Yes
\config | cucumber.yml
\features\amc\stage2\cpoe | cpoe_for_laboratory_orders.feature
cpoe_for_medication_orders.feature
cpoe_for_rediology_orders.feature
\features\amc\stage2\demographics | demographics.feature
\features\amc\stage2\electronic_notes | record_electronic_notes.feature
\features\amc\stage2\erx | generate_and_transmit_erx.feature
\features\amc\stage2\family_health_history | family_health_history.feature
\features\amc\stage2\generate_patient_list | generate_patient_list.feature
\features\amc\stage2\lab_results | incorporate_clinical_lab_results.feature
\features\amc\stage2\med_reconciliation | med_reconciliation.feature
\features\amc\stage2\patient_education | patient_education.feature
\features\amc\stage2\patient_electronic_access | patient_electronic_access.feature
\features\amc\stage2\preventive_care | preventive_care.feature
\features\amc\stage2\provide_clinical_summary | provide_clinical_summary.feature
\features\amc\stage2\smoking_status | smoking_status.feature
\features\amc\stage2\test_data | all test data (yml) files
\features\amc\stage2\vital_signs | vital_signs.feature
vital_signs_blood_pressure.feature
vital_signs_hight_weight.feature