## Slide 2
DR Systems - eHR Test Automation Plan

## Slide 3
Agenda
Scope
Plan and Milestones
Automation – DR Systems Need
Our Approach
Assumptions
Deliverables

## Slide 4
Automation – DR Systems need
Scope
Create new Automation framework for automating eHR
Automation framework should drive both Desktop Web and Mobile web application
Automating minimum 95% of eHR Web Regression Test suite
Automating minimum 95% of eHR Mobile Regression Test suite
Automated script should be executed against the below said environment
Setup Automation environment in DR Systems
Performance testing automation for identified scenarios of eHR application
Environment

## Slide 5
Desktop Web Automation Scope
Module | Section
AMC Stage1 | Stage 1 - CPOE Medication
 | Stage 1 - Demographic
 | Stage 1 - eRX
 | Stage 1 - Generate Patient List
 | Stage 1 - Med Allergy
 | Stage 1 - Med Reconciliation
 | Stage 1 - Medication List
 | Stage 1 - Patient Education
 | Stage 1 - Problem List
 | Stage 1 - Provide Clinical Summary
 | Stage 1 - Send Reminders
 | Stage 1 - Smoking Status
 | Stage 1 - Timely Access
 | Stage 1 - Transition Summary of Care
 | Stage 1 - Vital Signs

## Slide 6
Desktop Web Automation Scope
Module | Section
AMC Stage 2 | Stage 2 - CPOE
 | Stage 2 - Demographics
 | Stage 2 - Electronic Notes
 | Stage 2 - eRx
 | Stage 2 - Family Health History
 | Stage 2 - Generate Patient List
 | Stage 2 - Imaging Results
 | Stage 2 - Med Reconciliation
 | Stage 2 - Patient Education
 | Stage 2 - Patient Electronic Access
 | Stage 2 - Preventive Care
 | Stage 2 - Provide Clinical Summary
 | Stage 2 - Smoking Status
 | Stage 2 - Summary of Care
 | Stage 2 - Vitals Signs
Non Compliance | 
Measurement Attestations | 

## Slide 7
Desktop Web Automation Scope
Module | Section
Health Status | Allergies
 | Clinical Documents
 | Demographics
 | Family History
 | Immunization
 | Medications
 | Problems
 | Reconcile
 | Smoking
 | Syndromic Surveillance
 | Vitals
Order Entry or Results | Lab
 | Medications
 | Radiology
 | Reports
Visit Notes | Care Team Member
 | Visit Docs
 | Visit Notes

## Slide 8
Desktop Web Automation Scope
Module | Section
Tasks | Create Electronic Summary
 | Generate CQM Report
 | Generate Health Record
 | Generate Patient List
 | Generate Patient Reminder List
 | Patient Request Health Information
 | Resend Patient Reminder
 | Send Patient Reminders
Others | Setup
 | Select Patient
 | Emergency Access
 | Demographics
 | Select Patient
 | Clinical Summary

## Slide 9
Mobile Web Automation Scope
Module | Section
Mobile | Allergies
 | Family History
 | General
 | Medications
 | Problems
 | Smoking
 | Vitals
Module | Section
HL7 | Allergies
 | Imaging
 | Labs
 | Medications
 | Problems
 | Reports and Lay Letters
 | Smoking Status
 | Visits Patients
 | Vitals

## Slide 10
Test Suite Matrix – Desktop Web
 | Module Name | Sub Module | No. of Test Scenarios | No of Test Steps | Additional Test Steps expected | Total No. of Test Steps
Desktop - Web | AMC - Stage1 | General | 35 | 288 |  | 288
 |  | HC AMC Measures |  | 18 |  | 18
 |  | Stage 1 - Clinical Decision Support |  | 0 |  | 0
 |  | Stage 1 - CPOE Medication | 11 | 255 |  | 255
 |  | Stage 1 - Demographic | 9 | 199 |  | 199
 |  | Stage 1 - eRX | 3 | 35 |  | 35
 |  | Stage 1 - Generate Patient List | 2 | 18 |  | 18
 |  | Stage 1 - Med Allergy | 10 | 207 |  | 207
 |  | Stage 1 - Med Reconciliation | 4 | 139 |  | 139
 |  | Stage 1 - Medication List | 9 | 184 |  | 184
 |  | Stage 1 - Patient Education | 6 | 56 |  | 56
 |  | Stage 1 - Problem List | 10 | 190 |  | 190
 |  | Stage 1 - Provide Clinical Summary | 12 | 318 |  | 318
 |  | Stage 1 - Send Reminders | 9 | 271 |  | 271
 |  | Stage 1 - Smoking Status | 8 | 152 |  | 152
 |  | Stage 1 - Timely Access | 5 | 121 |  | 121
 |  | Stage 1 - Transition Summary of Care | 7 | 122 |  | 122
 |  | Stage 1 - Vital Signs | 33 | 650 |  | 650
 | AMC - Stage2 | Stage 2 - Clinical Decision Support |  |  |  | 0
 |  | Stage 2 - CPOE | 13 | 213 |  | 213
 |  | Stage 2 - Demographics | 9 | 198 |  | 198
 |  | Stage 2 - Electronic Notes | 7 | 130 |  | 130
 |  | Stage 2 - eRx | 4 | 78 |  | 78
 |  | Stage 2 - Family Health History | 8 | 187 |  | 187
 |  | Stage 2 - Generate Patient List | 2 | 18 |  | 18
 |  | Stage 2 - Imaging Results | 3 | 46 |  | 46
 |  | Stage 2 - Lab Results |  |  |  | 0
 |  | Stage 2 - Med Reconciliation | 4 | 21 |  | 21
 |  | Stage 2 - Patient Education | 3 | 79 |  | 79
 |  | Stage 2 - Patient Electronic Access | 8 | 219 |  | 219
 |  | Stage 2 - Preventive Care | 5 | 103 |  | 103
 |  | Stage 2 - Provide Clinical Summary | 5 | 133 |  | 133
 |  | Stage 2 - Smoking Status | 8 | 141 |  | 141
 |  | Stage 2 - Summary of Care | 8 | 109 |  | 109
 |  | Stage 2 - Vitals Signs | 25 | 508 |  | 508

## Slide 11
Test Suite Matrix – Desktop Web
 | Module Name | Sub Module | No. of Test Scenarios | No of Test Steps | Additional Test Steps expected | Total No. of Test Steps
Desktop - Web | Non Compliance |  | 43 | 128 | 216 | 344
 | Clinical Summary and CCD sent to Health Companion |  | 10 | 191 | 40 | 231
 | Clinical Summary or End of Exam |  | 44 | 573 |  | 573
 | Measurement Attestations |  | 14 | 162 |  | 162
 | Demographics |  | 6 | 25 | 10 | 35
 | Emergency Access |  | 10 | 73 |  | 73
 | Health Status | Allergies | 11 | 77 |  | 77
 |  | Clinical Documents | 9 | 105 |  | 105
 |  | Demographics | 7 | 40 |  | 40
 |  | Family History | 15 | 126 | 30 | 156
 |  | Immunization | 13 | 219 |  | 219
 |  | Medications | 8 | 70 |  | 70
 |  | Problems | 5 | 50 |  | 50
 |  | Reconcile | 11 | 177 |  | 177
 |  | Smoking | 13 | 69 |  | 69
 |  | Syndromic Surveillance | 6 | 60 |  | 60
 |  | Vitals | 26 | 196 |  | 196
 | MU Checklist | Allergies | 2 | 29 |  | 29
 |  | Demographics | 2 | 24 |  | 24
 |  | End of Exam or Clinical Summary | 38 | 214 |  | 214
 |  | Family History | 3 | 39 |  | 39
 |  | General | 1 | 5 |  | 5
 |  | Medications | 2 | 29 |  | 29
 |  | Problems | 2 | 29 |  | 29
 |  | Reconciliation | 3 | 77 |  | 77
 |  | Smoking Status | 2 | 19 |  | 19
 |  | Vitals | 2 | 25 |  | 25
 | Order Entry or Results | Lab | 14 | 96 |  | 96
 |  | Medications | 5 | 50 |  | 50
 |  | Radiology | 8 | 46 |  | 46
 |  | Reports |  |  |  | 0
 | Patient Portal |  | 8 | 28 | 50 | 78
 | Select Patient | Create Patient | 18 | 84 | 16 | 100
 |  | Exam | 6 | 33 |  | 33
 |  | Search | 6 | 20 |  | 20

## Slide 12
Test Suite Matrix – Desktop Web
 | Module Name | Sub Module | No. of Test Scenarios | No of Test Steps | Additional Test Steps expected | Total No. of Test Steps
Desktop - Web | Session and Security |  | 5 | 11 | 10 | 21
 | Set Up-Communications |  | 8 | 88 |  | 88
 | Set Up-Decision Support Rules |  | 54 | 999 |  | 999
 | Set Up-Eligible Professional |  | 18 | 64 | 28 | 92
 | Set Up-End of Exam or Visit Template |  | 2 | 9 | 4 | 13
 | Set Up-Other Data Administration | Clinic | 4 | 28 |  | 28
 |  | Drug Formulary | 9 | 80 |  | 80
 |  | Drug Interaction | 22 | 202 |  | 202
 |  | Facility, Site | 8 | 8 | 30 | 38
 | Set Up-Patient Educational Material |  | 17 | 205 |  | 205
 | Set Up - Safety Checker | Gadolinium |  | 213 |  | 213
 |  | Iodine |  | 165 |  | 165
 | Set Up-Site Administration | Audit Logs | 23 | 233 |  | 233
 |  | Manage Permissions | 3 | 56 |  | 56
 |  | Modules and Jobs | 4 | 63 |  | 63
 |  | Organization | 41 | 56 |  | 56
 |  | User Password Policy | 2 | 78 |  | 78
 |  | Users and Groups | 8 | 97 |  | 97
 | Tasks | Create Electronic Summary |  | 16 |  | 16
 |  | Generate CQM Report | 21 | 168 |  | 168
 |  | Generate Health Record | 3 | 20 |  | 20
 |  | Generate Patient List | 13 | 198 |  | 198
 |  | Generate Patient Reminder List | 6 | 30 |  | 30
 |  | Patient Request Health Information |  |  |  | 0
 |  | Resend Patient Reminder |  |  |  | 0
 |  | Send Patient Reminders | 30 | 240 |  | 240
 | Visit Notes | Care Team Member | 3 | 28 |  | 28
 |  | MongoDB | 3 | 10 |  | 10
 |  | Visit Docs | 8 | 28 |  | 28
 |  | Visit Notes | 9 | 128 |  | 128
 |  | Total | 1025 | 12243 | 650 | 12893

## Slide 13
Test Suite Matrix – Mobile, HL7, HC
 | Module Name | No of Test Scenarios | No of Test Steps | Additional Steps Expected | Total No of Steps
Mobile - Web | Allergies | 6 | 70 |  | 70
 | Family History | 12 | 130 |  | 130
 | General | 18 | 187 |  | 187
 | Medications | 6 | 73 |  | 73
 | Problems | 7 | 80 |  | 80
 | Smoking | 3 | 25 |  | 25
 | Vitals | 3 | 40 |  | 40
 | Total | 55 | 605 |  | 605
HL7 | Allergies | 10 | 33 |  | 33
 | Imaging | 1 | 5 |  | 5
 | Labs | 2 | 11 |  | 11
 | Medications | 7 | 24 |  | 24
 | Problems | 4 | 13 |  | 13
 | Reports and Lay Letters | 4 | 4 | 16 | 20
 | Smoking Status | 3 | 12 |  | 12
 | Visit_Patients | 11 | 51 |  | 51
 | Vitals | 4 | 18 |  | 18
 | Total | 46 | 171 | 16 | 187
HC | AutoEOE | 34 | 34 | 102 | 136
 | Auto-Reconcile Pre-Appointment | 4 | 4 | 12 | 16
 | Direct Messages | 3 | 3 | 9 | 12
 | General | 51 | 146 | 54 | 200
 | Permissions-Settings for sending info to HC | 2 | 25 |  | 25
 | Provider Portal | 26 | 73 |  | 73
 | Reports-Lay Letters and Delays | 28 | 166 |  | 166
 | Total | 148 | 451 | 177 | 628

## Slide 14
Automation Approach
Test Preparation
Walkthrough available regression test suite of eHR application
Create Automation environment and provide knowledge on the same to DR Systems QA
TAF Design
Create new Test Automation framework for eHR
Test Script Development
Identify the verification points for the regression test scenarios
Dry Run and Bug Fixing
Execute test automation scripts across different browsers in both Script development and Automation environment
Ongoing Maintenance
Rerun the Test Automation Suite developed in the previous phase
Convert the manual regression test scenarios to automated scripts
Ensure that the scripts are well handled for unexpected failures / invalid data
Identify and fix for any minor issues found
Identify and develop reusable components
Get confirmation on the verification points for each test case

## Slide 15
Automation Approach
Since Desktop Web and Mobile Web application are different, it will be good to have separate code for easy maintenance
HL7 and HC Integration test cases will be added to Desktop Web code base
The Test Automation framework created will be used for both Desktop Web and Mobile Web
Priority of the Automation modules are defined based on the below,
  Modules which are frequently used by the customers
  Modules which take more time to test
  Modules which are stable and might not have any major change
  Modules which got more issues during previous testing
Deliverables on each Milestone will be defined based on the above priority and the same will be shared/confirmed with eHR QA
Where the test case is not complete or the verification points cannot be found, a verification points document will be created and the same will be confirmed with eHR QA for test coverage
Automation scripts will be created by Aspire Systems using the development environment which will be setup at Aspire Systems.

## Slide 16
Automation Approach
Once Automation script development is complete for a Milestone, it will be moved to DR Systems Automation environment through Perforce and complete testing on agreed environment will be performed.
Any issues found with the script will be fixed.
An Automation traceability matrix will be provided for each milestone which will mention on the test cases covered in that milestone.
The Automation Test script acceptance by QA will also be tracked in the traceability matrix
There are no Smoke test cases available. So, the approach for smoke testing will be to select few main cases from the automated list and group them as a smoke list which can be used for sanity check during build release.
Based on the priority provided, eHR QA will check on each module and confirm on the test case coverage.
Any post prod issues will be checked for manual test case coverage and the same will be included in next automation milestone. Estimate for the same is not included here.

## Slide 17: Framework
browser
Env
hooks
Feature File
Step definition
Integration
Appium
Webdriver
Test Data
XLSX
YML
Reusable utility
Browser specific
Result specific
Action specific
Object Repository
Handle browser controls
Execution Report
EPF

## Slide 18
Tools / Framework - To be Used
Selenium WebDriver
RubyMine – IDE
Cucumber
Ruby Language
CI – Jenkins
CVS, Perforce – Version Control
Automation Issue Tracker - Any
Appium

## Slide 19
Assumptions
Assumptions
Test script development is planned on new automation Environment
The script development environment will be updated every week/biweekly based on the build release. The VM image will be transferred through FTP.
The estimates are provided considering tools mentioned in “Tools to be used” section
The estimates are provided considering there is no major application downtime
Number of browsers on which test automation scripts to dry run is assumed as 3 for Web-Windows, 1 for Web-MAC, 1 for Android
DR Systems QA will execute the developed test scripts in DRSYS Automation environment for approval
All required Licenses and hardware to be provided by DR Systems
Additional scenarios would still be derived by QA even during project execution stage considering test coverage needs. It will be added to QA Complete by DR Systems QA. Any impact to milestone delivery on the additional scenarios added will be informed and plan updated accordingly.
Script Maintenance will also include minor UI / functional changes which does not affect the script flow
Test Script development and testing will be done in the latest stable build

## Slide 20
Assumptions - Contd…
Assumptions
Workarounds considered during script development will be discussed with DR Systems QA before implementation
The project plan shown in the following slides is the initial and high level plan which will be revisited after two milestone completion. Changes if any will be updated, communicated and tracked
For initial few milestones, a small demo will be provided to DR Systems eHR QA team after few test cases are developed. This will help in better understanding of the automation process
Test Cases which will be created for new releases are not considered in this estimation
Major impact to AUT due to GUI / functional changes / technology upgrades will be considered as additional scope. Changes for the above is NOT factored in the estimates
Test Cases related to eHR integration with Unity will not be taken for automation as Unity is Windows based application and cannot be automated with the set of tools selected. The same can be automated with Unity Automation.

## Slide 21
Project Plan – High Level
Task Name | Duration | Start Date | Finish Date
TAF Creation | 12 days | 8/27/2014 | 9/11/2014
AMC Stage 1 | 92 days | 9/18/2014 | 1/23/2015
Part1 | 20 days | 9/18/2014 | 10/15/2014
Part2 | 25 days | 10/17/2014 | 11/20/2014
Part3 | 18 days | 11/21/2014 | 12/16/2014
Part4 | 24 days | 12/23/2014 | 1/23/2015
AMC Stage 2 | 55 days | 1/27/2015 | 4/13/2015
Part1 | 21 days | 1/27/2015 | 2/24/2015
Part2 | 19 days | 2/25/2015 | 3/23/2015
Part3 | 15 days | 3/24/2015 | 4/13/2015
Non Compliance | 10 days | 4/15/2015 | 4/28/2015
Mobile Web | 17 days | 4/30/2015 | 5/22/2015
Tasks | 19 days | 5/25/2015 | 6/18/2015
Measurement Attestations | 9 days | 6/19/2015 | 7/1/2015
HL7 | 15 days | 6/19/2015 | 7/9/2015

## Slide 22
Project Plan – Contd..
Task Name | Duration | Start Date | Finish Date
Health Companion | 17.5 days | 7/7/2015 | 7/30/2015
Clinical Summary | 20 days | 7/31/2015 | 8/27/2015
Health Status | 29.5 days | 8/28/2015 | 10/8/2015
Part1 | 14.5 days | 8/28/2015 | 9/17/2015
Part2 | 15 days | 9/17/2015 | 10/8/2015
MU Checklist | 14 days | 10/8/2015 | 10/28/2015
Select Patient/Demographics | 5 days | 10/29/2015 | 11/4/2015
Visit Notes/Results | 11 days | 11/6/2015 | 11/20/2015
Setup | 67 days | 11/23/2015 | 2/23/2016
Decision Support Rules | 22 days | 11/23/2015 | 12/22/2015
Setup - Part2 | 18 days | 12/29/2015 | 1/21/2016
Setup - Part3 | 22 days | 1/25/2016 | 2/23/2016
Emergency Access | 1.5 days | 2/24/2016 | 2/25/2016
Project Handover - Training, etc | 7 days | 2/25/2016 | 3/7/2016

## Slide 23
Delivery - Milestones
Milestones | Deliverables
1/23/2015 | AMC Stage 1
10/15/2014 | Part1
11/20/2014 | Part2
12/18/2014 | Part3
1/23/2015 | Part4
4/13/2015 | AMC Stage 2
2/24/2015 | Part1
3/23/2015 | Part2
4/13/2015 | Part3
4/28/2015 | Non Compliance
5/22/2015 | Mobile Web
6/18/2015 | Tasks
7/1/2015 | Measurement Attestations
7/9/2015 | HL7

## Slide 24
Milestones – Contd..
Milestones | Deliverables
7/30/2015 | Health Companion
8/27/2015 | Clinical Summary
10/8/2015 | Health Status
9/17/2015 | Part1
10/8/2015 | Part2
10/28/2015 | MU Checklist
11/4/2015 | Select Patient/Demographics
11/20/2015 | Visit Notes/Results
2/23/2016 | Setup
12/22/2015 | Decision Support Rules
1/21/2016 | Setup - Part2
2/23/2016 | Setup - Part3
2/25/2016 | Emergency Access

## Slide 25
Monthly delivery Graph
Chart: Monthly Delivery Rate
| 41883 | 41913 | 41944 | 41974 | 42005 | 42036 | 42064 | 42095 | 42125 | 42156 | 42186 | 42217 | 42248 | 42278 | 42309 | 42339 | 42370 | 42401
Monthly Test Steps Creation | 600 | 630 | 700 | 725 | 750 | 750 | 780 | 800 | 750 | 750 | 800 | 800 | 850 | 850 | 800 | 800 | 850 | 850
Monthly Average | 600 | 615 | 643 | 664 | 681 | 693 | 705 | 717 | 721 | 724 | 730 | 736 | 745 | 753 | 756 | 758 | 764 | 769

## Slide 26
Delivery
As part of Milestone delivery
Automation Scripts [Checked in through Perforce]
Verification Points confirmation document
Automation traceability document with test cases details released in the Milestone
As part of complete project delivery
User Guide document to help in maintenance
Tools/Framework setup document
Complete list of Automation traceability
Complete list of Verification points added
Framework details document
Automation Scripts

## Slide 27
Appendix
Detailed Scope and Estimates are available in the attached document
Automation traceability document
Verification Points Confirmation document

## Slide 28: Thank You