## Summary
Summary
MileStone | Delivery Details | Planned |  | Actuals |  | Test Scenario Count |  | Acceptance Status ( by DRSYS QA)
|  | Start Date | End Date | Start date | End Date | Planned | Actual
Milestone 1 | AMC - Stage 2 - Part 1 | 2014-09-12 | 2014-10-23 | 2014-09-12 | 2014-10-20 | 45 | 45
Milestone 2 | AMC - Stage 2 - Part 2 | 2014-10-24 | 2014-11-24 | 2014-10-21 | 2014-11-24 | 48 | 48
Milestone 3 | AMC - Stage 2 - Part 3 | 2014-11-25 | 2014-12-16 | 2014-11-25 | 2014-12-15 | 73 | 73
Milestone 4 | AMC - Stage 1 - Part 1 | 2014-12-17 | 2015-01-16 | 2014-12-16 | 2015-01-12 | 37 | 37
Milestone 5 | AMC - Stage 1 - Part 2 | 2015-01-19 | 2015-02-19 | 2015-01-13 | 2015-02-09 | 49 | 49
Milestone 6 | AMC - Stage 1 - Part 3 |  |  |  |  | 38 | 38
Milestone 7
Milestone 8 | Non Compliance |  |  |  |  | 44 | 44
Milestone 9
Milestone 10 | Mobile Test Cases |  |  |  |  | 35 | 35
Milestone 11
Milestone 12
Milestone 13
Milestone 14
Milestone 15
Milestone 16
Milestone 17
Milestone 18
Milestone 19
Milestone 20
Milestone 21
Milestone 22
Milestone 23
|  |  | Total Count |  |  | 369 | 369

## MileStone1
Milestone 1 Delivery Details
QC Test Scenario ID | Section | Title | Delivered | Actual Milestone | Acceptance Status ( by DRSYS QA) | Accepted By | Accepted Date
221 | CPOE - Medication Orders | CPOE for Medication Orders measure does not take into account deleted medications. | Yes | Milestone1
5793 | CPOE - Medication Orders | CPOE Medications does not take into account Inactive Medications on Health Status tab | Yes | Milestone1
5794 | CPOE - Medication Orders | CPOE for Medication Orders measure does not take into account cancelled medication orders. | Yes | Milestone1
703 | CPOE - Medication Orders | Denominator for CPOE for medication orders Stage 2 AMC measure. | Yes | Milestone1
704 | CPOE - Medication Orders | Numerator for CPOE for medication orders Stage 2 AMC measure. | Yes | Milestone1
5805 | CPOE - Medication Orders | Help text and Requirement for CPOE for Medications Orders. | Yes | Milestone1
223 | CPOE - Laboratory Orders | CPOE for laboratory orders measure does not take into account cancelled laboratory orders. | Yes | Milestone1
4846 | CPOE - Laboratory Orders | CPOE for laboratory orders Stage 2 does not consider orders placed outside reporting period. | Yes | Milestone1
707 | CPOE - Laboratory Orders | Denominator for CPOE for laboratory orders Stage 2 AMC measure. | Yes | Milestone1
5804 | CPOE - Laboratory Orders | Help text and Requirement for Stage 2 CPOE for laboratory orders. | Yes | Milestone1
708 | CPOE - Laboratory Orders | Numerator for CPOE for laboratory orders Stage 2 AMC measure. | Yes | Milestone1
222 | CPOE - Radiology Orders | CPOE for radiology orders measure does not take into account cancelled radiology orders. | Yes | Milestone1
4847 | CPOE - Radiology Orders | CPOE for radiology orders Stage 2 measure does not take into account orders outside RP. | Yes | Milestone1
705 | CPOE - Radiology Orders | Denominator for CPOE for radiology orders Stage 2 AMC measure. | Yes | Milestone1
5806 | CPOE - Radiology Orders | Help text and Requirement column for Stage 2 CPOE for Radiology Orders. | Yes | Milestone1
706 | CPOE - Radiology Orders | Numerator for CPOE for radiology orders Stage 2 AMC measure. | Yes | Milestone1
4789 | Demographics | Demographics Stage 2 AMC measure. (Negative Scenarios) | Yes | Milestone1
4788 | Demographics | Demographics Stage 2 AMC measure. (Positive Scenario) | Yes | Milestone1
4787 | Demographics | Demographics Stage 2 AMC measure does not take into account patients with inactive visits. | Yes | Milestone1
4786 | Demographics | Demographics Stage 2 AMC measure does not take into account Inpatients. | Yes | Milestone1
4785 | Demographics | Demographics Stage 2 AMC measure does not take into account non face-to-face patients. | Yes | Milestone1
4784 | Demographics | Demographics Stage 2 AMC measure does not take into account patients seen outside reporting period. | Yes | Milestone1
192 | Demographics | Help text and Requirement for Stage 2 Demographics AMC measure. | Yes | Milestone1
4793 | Record Electronic Notes | Record Electronic Notes Stage 2 AMC measure does not account patients with inactive visit. | Yes | Milestone1
4792 | Record Electronic Notes | Record Electronic Notes Stage 2 AMC measure does not account Inpatients. | Yes | Milestone1
4791 | Record Electronic Notes | Record Electronic Notes Stage 2 AMC measure does not account non face-to-face patients. | Yes | Milestone1
4790 | Record Electronic Notes | Record Electronic Notes Stage 2 AMC measure does not account patients seen outside reporting period. | Yes | Milestone1
678 | Record Electronic Notes | Record Electronic Notes stage 2 AMC measure. | Yes | Milestone1
676 | Record Electronic Notes | Help text and Requirement column value for Record Electronic Notes stage 2 AMC measure. | Yes | Milestone1
709 | Generate and transmit eRx | Denominator for Generate and transmit eRx stage 2 AMC measure. | Yes | Milestone1
5811 | Generate and transmit eRx | Generate and transmit eRx does not take into account orders created outside reporting period. | Yes | Milestone1
25 | Generate and transmit eRx | Help text for e-Prescribing measure and Threshold measure in AMC stage 2 report. | Yes | Milestone1
710 | Generate and transmit eRx | Numerator for Generate and transmit eRx stage 2 AMC measure. | Yes | Milestone1
5812 | Generate and transmit eRx | Stage 2 Generate and transmit eRx does not take into account orders for controlled substances. | Yes | Milestone1
4796 | Family Health History | Family Health History does not account Inpatients. | Yes | Milestone1
4797 | Family Health History | Family Health History does not account patients with inactive status. | Yes | Milestone1
4794 | Family Health History | Family Health History does not account for patients seen outside reporting period. | Yes | Milestone1
4795 | Family Health History | Family Health History does not account non face-to-face patients. | Yes | Milestone1
402 | Family Health History | Family Health History stage 2 measure - Coded Family History | Yes | Milestone1
5754 | Family Health History | Family Health History stage 2 measure - More than 1 visit | Yes | Milestone1
5752 | Family Health History | Family Health History stage 2 measure - None Known | Yes | Milestone1
5753 | Family Health History | Family Health History stage 2 measure - Uncoded Family History | Yes | Milestone1
5755 | Family Health History | Family History Stage 2 does not take into account deleted Family History. | Yes | Milestone1
2184 | Family Health History | Family History Stage 2 does not take into account Inactive Family History. | Yes | Milestone1
396 | Family Health History | Help text and Requirement for Family Health History AMC stage 2 measure. | Yes | Milestone1

## MileStone2
Milestone 2 Delivery Details
QC Test Scenario ID | Section | Title | Delivered | Actual Milestone | Acceptance Status ( by DRSYS QA) | Accepted By | Accepted Date | Comments
567 | Generate Patient List | Help text and Requirement for generate Patient List AMC stage 2 measure | Yes | Milestone2
598 | Generate Patient List | Verification of Generate Patient List stage 2 AMC measure | Yes | Milestone2
669 | Patient Education | Help text and Requirement for Patient Education AMC stage 2 measure | Yes | Milestone2
6243 | Patient Education | Patient Education Material for patients with office visits within reporting period | Yes | Milestone2
6244 | Patient Education | Patient Education Material for patients with no office visits within reporting period | Yes | Milestone2
6245 | Patient Education | Patient Education does not consider period.patients seen outside reporting | Yes | Milestone2
6246 | Patient Education | Patient Education does not consider patients with non face-to-face visits | Yes | Milestone2
6247 | Patient Education | Patient Education does not consider patients with inpatient exams | Yes | Milestone2
6248 | Patient Education | Patient Education does not consider patients with inactive exams | Yes | Milestone2
666 | Preventive Care | Help text and Requirement column value for Preventive Care stage 2 AMC measure | Yes | Milestone2
668 | Preventive Care | Preventive Care stage 2 AMC measure takes into account the number of patients who have had 2 or more office visits and who were sent a reminder per patient preference | Yes | Milestone2
3229 | Preventive Care | Send button for Preventive Care AMC measure does not display when current date is not within reporting period | Yes | Milestone2
6627 | Preventive Care | Preventive Care does take into account patients seen outside reporting period | Yes | Milestone2
6628 | Preventive Care | Preventive Care does take into account for non face-to-face patients | Yes | Milestone2
6629 | Preventive Care | Preventive Care does not account Inpatients visits seen within reporting period | Yes | Milestone2
6630 | Preventive Care | Preventive Care does not take into account for patients with inactive visit | Yes | Milestone2
6631 | Preventive Care | Preventive Care does not account for patients who donot want receive reminders | Yes | Milestone2
6632 | Preventive Care | Preventive Care does not account patients with only 1 visits within 24 months prior to RP | Yes | Milestone2
61 | Smoking Status | Help text and threshold measure for smoking status measure on AMC stage 2 report | Yes | Milestone2
249 | Smoking Status | Verify Smoking Status stage 2 AMC measure | Yes | Milestone2
4798 | Smoking Status | Smoking Status Stage 2 AMC measure does not account for patients seen outside reporting period | Yes | Milestone2
4799 | Smoking Status | Smoking Status Stage 2 AMC measure does not take into account non face-to-face patients | Yes | Milestone2
4800 | Smoking Status | Smoking Status Stage 2 AMC measure does not take into account Inpatients | Yes | Milestone2
4801 | Smoking Status | Smoking Status Stage 2 AMC measure does not take into account patients with inactive visits | Yes | Milestone2
4802 | Smoking Status | Smoking status does not account for patients less than 13 years of age | Yes | Milestone2
6242 | Lab Results | Help text and Requirement for Stage 2 Incorporate Clinical Lab Results AMC measure | Yes | Milestone2
6227 | Lab Results | Stage 2 Incorporated Clinical Lab Results takes into account manually entered numeric results | Yes | Milestone2
6228 | Lab Results | Stage 2 Lab Results takes into account manually entered positive lab results | Yes | Milestone2
6229 | Lab Results | Stage 2 Lab Results takes into account manually entered negative lab results | Yes | Milestone2
6230 | Lab Results | Stage 2 Lab Results does not take into account results which are not positive, negative or numeric | Yes | Milestone2
6231 | Lab Results | Stage 2 Lab Results does not take into account manual results added outside reporting period | Yes | Milestone2
6232 | Lab Results | Stage 2 Lab Results does not take into account orders with cancelled status | Yes | Milestone2
6233 | Lab Results | Stage 2 Lab Results does not take into account lab results with inactive status | Yes | Milestone2
6234 | Lab Results | Stage 2 Lab Results does not take into account lab results deleted from system | Yes | Milestone2
6235 | Lab Results | Stage 2 Lab Results for multiple manually entered lab orders and lab results within reporting period | Yes | Milestone2
6549 | Lab Results | Stage 2 Lab results does not take into account uncoded (save as typed) lab results | Yes | Milestone2
717 | Med Reconciliation | Help text and threshold for Medication Reconciliation Stage 2 AMC measure. | Yes | Milestone2
3398 | Med Reconciliation | Stage 2 Med Reconciliation does not take into account patients seen by EP outside reporting period. | Yes | Milestone2
5511 | Med Reconciliation | Stage 2 Med Reconciliation does not take into account non Face to Face patients. | Yes | Milestone2
5512 | Med Reconciliation | Stage 2 Med Reconciliation does not take into account Inpatients seen by EP during reporting period. | Yes | Milestone2
5513 | Med Reconciliation | Stage 2 Med Reconciliation does not take into account patients with inactive visit during RP | Yes | Milestone2
5514 | Med Reconciliation | Stage 2 Med Reconciliation with first time visit and reconciliation by adding medication. | Yes | Milestone2
5515 | Med Reconciliation | Stage 2 Med Reconciliation with first time visit and reconciliation clicking None Known. | Yes | Milestone2
5516 | Med Reconciliation | Stage 2 Med Reconciliation with not first time visit with EP and TOC. | Yes | Milestone2
6563 | Med Reconciliation | Stage 2 Medication Reconciliation delete scenario - 1 | Yes | Milestone2
6564 | Med Reconciliation | Stage 2 Medication Reconciliation delete scenario - 2 | Yes | Milestone2
6565 | Med Reconciliation | Stage 2 Medication Reconciliation delete scenario - 3 | Yes | Milestone2
6566 | Med Reconciliation | Stage 2 Medication Reconciliation delete scenarios - 4 | Yes | Milestone2

## Milestone3
Milestone 3 Delivery Details
QC Test Scenario ID | Section | Title | Delivered | Actual Milestone | Acceptance Status ( by DRSYS QA) | Accepted By | Accepted Date | Comments
4236 | Patient Electronic Access | Patient Electronic Access Stage 2 AMC measure (+ve scenario only considering exams on weekdays) | Yes | Milestone3
4244 | Patient Electronic Access | Help text and requirement column for Patient Electronic Access Stage 2 AMC measure | Yes | Milestone3
4245 | Patient Electronic Access | Patient Electronic Access Stage 2 AMC measure (Negative scenario with exam on weekdays) | Yes | Milestone3
4246 | Patient Electronic Access | Patient Electronic Access Stage 2 measure does not account visits outside reporting period | Yes | Milestone3
4247 | Patient Electronic Access | Patient Electronic Access Stage 2 does not take into account visits with 'Count for MU' unchecked | Yes | Milestone3
4248 | Patient Electronic Access | Patient Electronic Access Stage 2 measure does not take into account Inpatient patients | Yes | Milestone3
4249 | Patient Electronic Access | Patient Electronic Access Stage 2 measure does not consider inactive visits | Yes | Milestone3
6598_1 | Patient Electronic Access | Verification of Positive scenarios considering weekends in Patient Electronic Access Stage 2 AMC measure - 124 hours | Yes | Milestone3
6598_2 | Patient Electronic Access | Verification of Positive scenarios considering weekends in Patient Electronic Access Stage 2 AMC measure - 143.5 hours & 119.5 hours | Yes | Milestone3
6598_3 | Patient Electronic Access | Verification of Positive scenarios considering weekends in Patient Electronic Access Stage 2 AMC measure - 105 hours | Yes | Milestone3
6598_4 | Patient Electronic Access | Verification of Positive scenarios considering weekends in Patient Electronic Access Stage 2 AMC measure - 143.5 hours | Yes | Milestone3
6603_1 | Patient Electronic Access | Verification of Positive scenarios considering US Federal Holidays in Patient Electronic Access Stage 2 AMC measure - on US Federal Holiday | Yes | Milestone3
6603_2 | Patient Electronic Access | Verification of Positive scenarios considering US Federal Holidays in Patient Electronic Access Stage 2 AMC measure - 2 days prior to US Federal Holiday | Yes | Milestone3
6676_1 | Patient Electronic Access | Verification of Negative scenarios only considering exam on weekends in Patient Electronic Access Stage 2 AMC measure - on saturday & Sunday | Yes | Milestone3
6676_2 | Patient Electronic Access | Verification of Negative scenarios only considering exam on weekends in Patient Electronic Access Stage 2 AMC measure - on Thursday | Yes | Milestone3
6677_1 | Patient Electronic Access | Verification of Negative scenarios with exam on US Federal Holidays in Patient Electronic Access Stage 2 AMC measure - on US Federal Holiday | Yes | Milestone3
6677_2 | Patient Electronic Access | Verification of Negative scenarios with exam on US Federal Holidays in Patient Electronic Access Stage 2 AMC measure - 2 days prior to US Federal Holiday | Yes | Milestone3
500 | Provide Clinical Summary | Provide Clinical Summary AMC stage 2 measure. (+ve scenarios with exam on weekdays) | Yes | Milestone3
1826_1 | Provide Clinical Summary | Verification of Positive scenarios considering exams on Weekends in Provide Clinical Summary Stage 2 AMC measure - on Saturday | Yes | Milestone3
1826_2 | Provide Clinical Summary | Verification of Positive scenarios considering exams on Weekends in Provide Clinical Summary Stage 2 AMC measure - on saturday & Sunday | Yes | Milestone3
1826_3 | Provide Clinical Summary | Verification of Positive scenarios considering exams on Weekends in Provide Clinical Summary Stage 2 AMC measure - on Sunday | Yes | Milestone3
1826_4 | Provide Clinical Summary | Verification of Positive scenarios considering exams on Weekends in Provide Clinical Summary Stage 2 AMC measure - 60 hours & Friday | Yes | Milestone3
1826_5 | Provide Clinical Summary | Verification of Positive scenarios considering exams on Weekends in Provide Clinical Summary Stage 2 AMC measure - 71 hours & Friday | Yes | Milestone3
1827_1 | Provide Clinical Summary | Verification of Positive scenario with exam created on US Federal Holidays in Provide Clinical Summary Stage 2 AMC measure - 25 hours | Yes | Milestone3
1827_2 | Provide Clinical Summary | Verification of Positive scenario with exam created on US Federal Holidays in Provide Clinical Summary Stage 2 AMC measure - 47 hours | Yes | Milestone3
6678 | Provide Clinical Summary | Stage 2 Provide Clinical Summary does not take into account exams created outside reporting period | Yes | Milestone3
6679 | Provide Clinical Summary | Stage 2 Provide Clinical Summary does not take into account patient with non face-to-face visits | Yes | Milestone3
6680 | Provide Clinical Summary | Stage 2 Provide Clinical Summary does not take into account patient with Inpatient visit | Yes | Milestone3
6681 | Provide Clinical Summary | Stage 2 Provide Clinical Summary does not take into account patient with Inactive visit | Yes | Milestone3
6682_1 | Provide Clinical Summary | Verification of Negative scenario with exam created on US Federal Holidays in Provide Clinical Summary Stage 2 AMC measure - on US Federal Holiday | Yes | Milestone3
6682_2 | Provide Clinical Summary | Verification of Negative scenario with exam created on US Federal Holidays in Provide Clinical Summary Stage 2 AMC measure - 1 day prior to US Federal Holiday | Yes | Milestone3
6683_1 | Provide Clinical Summary | Verification of Negative scenarios with exams on weekends in Provide Clinical Summary stage 2 AMC measure - on saturday & Sunday | Yes | Milestone3
6683_2 | Provide Clinical Summary | Verification of Negative scenarios with exams on weekends in Provide Clinical Summary stage 2 AMC measure - on Friday | Yes | Milestone3
6684 | Provide Clinical Summary | Provide Clinical Summary stage 2 AMC measure (-ve scenario with exams created on weekdays) | Yes | Milestone3
498 | Provide Clinical Summary | Help text and Threshold value for Provide Clinical Summary AMC stage 2 measure | Yes | Milestone3
36 | Vital Signs | Vital Signs stage 2 AMC measure - patient greater or equal to 3 yrs | Yes | Milestone3
4805 | Vital Signs | Vital Signs Stage 2 AMC - visit outside RP and patients greater or equal to 3 years | Yes | Milestone3
4806 | Vital Signs | Vital Signs Stage 2 AMC - Not Face-to-Face visit and patients greater or equal to 3 years | Yes | Milestone3
4807 | Vital Signs | Vital Signs Stage 2 AMC - Inpatient visit and patients greater or equal to 3 years | Yes | Milestone3
4808 | Vital Signs | Vital Signs Stage 2 AMC - Inactive visit and patients greater or equal to 3 years | Yes | Milestone3
4809 | Vital Signs | Vitals Signs for patients greater than or equal to 3 years (negative scenarios) | Yes | Milestone3
4810 | Vital Signs | Vitals Signs for patients less than 3 years (negative scenarios) | Yes | Milestone3
6604 | Vital Signs | Vital Signs stage 2 AMC measure - (patient with multiple visits) | Yes | Milestone3
6605 | Vital Signs | Vital Signs stage 2 AMC measure - patient less than 3 yrs | Yes | Milestone3
6606 | Vital Signs | Vital Signs Stage 2 AMC - Inactive visit and patients less than 3 years | Yes | Milestone3
6620 | Vital Signs | Vital Signs Stage 2 AMC - visit outside RP and patients less than 3 years | Yes | Milestone3
6621 | Vital Signs | Vital Signs Stage 2 AMC - Inpatient visit and patients less than 3 years | Yes | Milestone3
6622 | Vital Signs | Vital Signs Stage 2 AMC - Not Face-to-Face visit and patients less than 3 years | Yes | Milestone3
6624 | Vital Signs | Help text and Requirement for Stage 2 Vitals Signs AMC measure | Yes | Milestone3
235 | Vital Signs - Blood Pressure | Vital Signs - Blood Pressure stage 2 AMC measure | Yes | Milestone3
4811 | Vital Signs - Blood Pressure | Vital Signs - Blood Pressure does not account for patients outside reporting period | Yes | Milestone3
4812 | Vital Signs - Blood Pressure | Vital Signs - Blood Pressure does not account for non face-to-face patients | Yes | Milestone3
4813 | Vital Signs - Blood Pressure | Vital Signs - Blood Pressure does not account for Inpatients | Yes | Milestone3
4814 | Vital Signs - Blood Pressure | Vital Signs - Blood Pressure does not account patients having inactive visit | Yes | Milestone3
4815 | Vital Signs - Blood Pressure | Vital Signs - Blood Pressure does not account patients less than 3 years old | Yes | Milestone3
4816 | Vital Signs - Blood Pressure | Vital Signs - Blood Pressure does not account patients greater than 3 years old with no BP recorded | Yes | Milestone3
6623 | Vital Signs - Blood Pressure | Help text and Requirement for Stage 2 Vital Signs - Blood Pressure | Yes | Milestone3
6625 | Vital Signs - Blood Pressure | Vital Signs - Blood Pressure stage 2 AMC measure (multiple visits) | Yes | Milestone3
213 | Vital Signs - Blood Pressure | Height and weight and Blood Pressure are recorded as 2 separate measure for AMC stage 2 report | Yes | Milestone3
233 | Vital signs - Height and weight | Vital signs - Height and weight stage 2 AMC measure | Yes | Milestone3
4817 | Vital signs - Height and weight | Vital signs - Height and weight stage 2 measure does not account for patients seen outside reporting | Yes | Milestone3
4818 | Vital signs - Height and weight | Vital signs - Height and weight stage 2 measure does not account for non face-to-face patients | Yes | Milestone3
4819 | Vital signs - Height and weight | Vital signs - Height and weight stage 2 measure does not account for Inpatients | Yes | Milestone3
4820 | Vital signs - Height and weight | Vital signs - Height and weight stage 2 measure does not account for patients with inactive visits | Yes | Milestone3
4821 | Vital signs - Height and weight | Vital signs - Height and weight does not account for patients with no height or weight recorded | Yes | Milestone3
6626 | Vital signs - Height and weight | Vital signs - Height and weight stage 2 AMC measure (multiple visits) | Yes | Milestone3
38 | Vital signs - Height and weight | Help text and Requirement for Stage 2 Vital Signs - Height and Weight AMC measure | Yes | Milestone3
6236 | Incorporated Clinical Lab Results (HL7 part) | Stage 2 Incorporated Clinical Lab Results takes into account numeric lab results created by HL7 | Yes | Milestone3
6237 | Incorporated Clinical Lab Results (HL7 part) | Stage 2 Incorporated Clinical Lab Results takes into account positive lab results created by HL7 | Yes | Milestone3
6238 | Incorporated Clinical Lab Results (HL7 part) | Stage 2 Incorporated Clinical Lab Results takes into account negative lab results created by HL7 | Yes | Milestone3
6239 | Incorporated Clinical Lab Results (HL7 part) | Stage 2 Lab Results does not consider HL7 results which are not positive, negative or numeric | Yes | Milestone3
6240 | Incorporated Clinical Lab Results (HL7 part) | Stage 2 Lab Results does not consider HL7 lab orders and results added outside reporting period | Yes | Milestone3
6241 | Incorporated Clinical Lab Results (HL7 part) | Stage 2 Incorporate Clinical Lab Results for HL7 lab order having multiple results | Yes | Milestone3

## Milestone4
Milestone 4 Delivery Details
QC Test Scenario ID | Section | Title | Delivered | Actual Milestone | Acceptance Status ( by DRSYS QA) | Accepted By | Accepted Date | Comments
700 | CPOE for Medication Order | CPOE for medication orders Stage 1 AMC measure | Yes | Milestone4
4840 | CPOE for Medication Order | CPOE for Med Orders does not take into account patients seen outside reporting period | Yes | Milestone4
4841 | CPOE for Medication Order | CPOE for Med Orders does not take into account non face-to-face patients | Yes | Milestone4
4842 | CPOE for Medication Order | CPOE for Med Orders does not take into account Inpatients | Yes | Milestone4
4843 | CPOE for Medication Order | CPOE for Med Orders does not take into account patients with inactive visits | Yes | Milestone4
4844 | CPOE for Medication Order | CPOE Meds Stage 1 does not take into account inactive medications on Medication List | Yes | Milestone4
6692 | CPOE for Medication Order | CPOE Medications Orders does not take into account cancelled CPOE medications orders | Yes | Milestone4
6693 | CPOE for Medication Order | CPOE Meds Stage 1 does not take into account deleted Medications under Medication Lists | Yes | Milestone4
702 | CPOE for Medication Orders - Alternate | CPOE for medication orders - Alternate Stage 1 AMC measure | Yes | Milestone4
4845 | CPOE for Medication Orders - Alternate | CPOE for Med orders - Alternate Stage 1 does not take into account orders created outside RP | Yes | Milestone4
6696 | CPOE for Medication Orders - Alternate | CPOE for Medication Orders - Alternate Stage 1 does not take into account inactive medications | Yes | Milestone4
6697 | CPOE for Medication Orders - Alternate | CPOE for Medication Orders - Alternate Stage 1 does not take into account deleted medications | Yes | Milestone4
6698 | CPOE for Medication Orders - Alternate | CPOE for Medication Orders - Alternate Stage 1 does not take into account cancelled med orders | Yes | Milestone4
3554 | Demographics | Help text and Requirement for Stage 1 Demographics measure | Yes | Milestone4
4251 | Demographics | Demographics Stage 1 AMC measure does not account visits outside reporting period | Yes | Milestone4
4252 | Demographics | Demographics Stage 1 AMC measure does not account Inpatient | Yes | Milestone4
4253 | Demographics | Demographics Stage 1 AMC measure does not account non Face-to-Face patients | Yes | Milestone4
4254 | Demographics | Demographics Stage 1 AMC measure does not account patients with Inactive Exams | Yes | Milestone4
4470 | Demographics | Demographics Sage 1 AMC measure (Positive Scenarios) | Yes | Milestone4
4476 | Demographics | Demographics Sage 1 AMC measure (Negative Scenarios) | Yes | Milestone4
595 | Generate Patient List | Help text for Generate Patient List stage 1 AMC measure | Yes | Milestone4
596 | Generate Patient List | Generate Patient List stage 1 AMC measure | Yes | Milestone4
3589 | Medication Allergy List | Medication Allergy Stage 1 AMC measure does not take into account inactive allergies | Yes | Milestone4
3590 | Medication Allergy List | Help text and Requirement for Stage 1 Medication Allergy List AMC measure | Yes | Milestone4
4638 | Medication Allergy List | Medication Allergy Stage 1 AMC measure does not account patients seen outside EHR reporting period | Yes | Milestone4
4639 | Medication Allergy List | Medication Allergy Stage 1 AMC measure does not account for no Face -to-face patients | Yes | Milestone4
4747 | Medication Allergy List | Medication Allergy Stage 1 AMC measure does not account for Inpatient | Yes | Milestone4
4748 | Medication Allergy List | Medication Allergy Stage 1 AMC measure does not account for patients with Inactive visit | Yes | Milestone4
4749 | Medication Allergy List | Medication Allergy Stage 1 AMC measure | Yes | Milestone4
4750 | Medication Allergy List | Medication Allergy List Stage 1 AMC measure does not account patients with allergy type of 'Other' | Yes | Milestone4
3592 | Medication List | Medication List Stage 1 AMC measure does not take into account inactive medications | Yes | Milestone4
3593 | Medication List | Help text and Requirement for Stage 1 Medication List AMC measure | Yes | Milestone4
4751 | Medication List | Medication List Stage 1 AMC measure does not account patients seen outside reporting period | Yes | Milestone4
4752 | Medication List | Medication List Stage 1 AMC measure does not account non Face-to-Face patients | Yes | Milestone4
4753 | Medication List | Medication List Stage 1 AMC measure does not account for Inpatients | Yes | Milestone4
4754 | Medication List | Medication List Stage 1 AMC measure does not account patients with inactive visits | Yes | Milestone4
4755 | Medication List | Medication List Stage 1 AMC measure | Yes | Milestone4

## Milestone5
Milestone 5 Delivery Details
QC Test Scenario ID | Section | Title | Delivered | Actual Milestone | Acceptance Status ( by DRSYS QA) | Accepted By | Accepted Date | Comments
535 | Generate and Transmit eRx | Denominator value for Generate and transmit eRX stage 1 AMC measure | Yes | Milestone5
536 | Generate and Transmit eRx | Numerator value for Generate and transmit eRx stage 1 AMC measure | Yes | Milestone5
3555 | Generate and Transmit eRx | Help text and Requirement for 'Generate and Transmit eRx' Stage 1 AMC measure | Yes | Milestone5
6723 | Generate and Transmit eRx | Stage 1 eRX does not take into account orders placed outside reporting period | Yes | Milestone5
6724 | Generate and Transmit eRx | Stage 1 eRx does not take into account orders for controlled substances | Yes | Milestone5
5003 | Medication Reconciliation | Stage 1 Med Reconciliation does not consider visits outside reporting period | Yes | Milestone5
5005 | Medication Reconciliation | Stage 1 Medication Reconciliation does not take into account non Face to Face visits | Yes | Milestone5
5006 | Medication Reconciliation | Stage 1 Medication Reconciliation does not take into account for Inpatients | Yes | Milestone5
5007 | Medication Reconciliation | Stage 1 Medication Reconciliation does not take into account Inactive visits within reporting period | Yes | Milestone5
5011 | Medication Reconciliation | Stage 1 Med Reconciliation where reconciliation by adding medication on Health Status | Yes | Milestone5
5012 | Medication Reconciliation | Stage 1 Med Reconciliation where reconciliation by clicking on None Known within RP | Yes | Milestone5
5509 | Medication Reconciliation | Stage 1 Med Reconciliation where reconciling medication from TOC | Yes | Milestone5
5510 | Medication Reconciliation | Help text and Requirement value for Stage 1 Medication Reconciliation | Yes | Milestone5
6559 | Medication Reconciliation | Stage 1 Medication Reconciliation delete scenario - 1 | Yes | Milestone5
6560 | Medication Reconciliation | Stage 1 Medication Reconciliation delete scenario - 2 | Yes | Milestone5
6561 | Medication Reconciliation | Stage 1 Medication Reconciliation delete scenario - 3 | Yes | Milestone5
6562 | Medication Reconciliation | Stage 1 Medication Reconciliation delete scenario - 4 | Yes | Milestone5
673 | Patient Specific Education Resources | Patient Specific Education Resources stage 1 AMC measure | Yes | Milestone5
3802 | Patient Specific Education Resources | Help text and Requirement column for Stage 1 Patient Specific Education Resources AMC measure | Yes | Milestone5
4849 | Patient Specific Education Resources | Patient Education Stage 1 does not take into account patients seen outside reporting period | Yes | Milestone5
4909 | Patient Specific Education Resources | Patient Education Stage 1 AMC does not take into account non face-to-face patients | Yes | Milestone5
4912 | Patient Specific Education Resources | Patient Education Stage 1 AMC measure does not take into account Inpatients | Yes | Milestone5
6729 | Patient Specific Education Resources | Patient Education Stage 1 AMC measure does not take into account patients with inactive visits | Yes | Milestone5
3594 | Problem List | Problem List Stage 1 AMC measure does account inactive problems | Yes | Milestone5
3595 | Problem List | Help text and Requirement column for Stage 1 Problem List AMC measure | Yes | Milestone5
4756 | Problem List | Problem List Stage 1 AMC measure does not account for patients seen outside reporting period | Yes | Milestone5
4757 | Problem List | Problem List Stage 1 AMC measure does not account non Face-to-Face patients | Yes | Milestone5
4758 | Problem List | Problem List Stage 1 AMC measure does not account for Inpatients | Yes | Milestone5
4759 | Problem List | Problem List Stage 1 AMC measure does not account for patients with inactive visits | Yes | Milestone5
4760 | Problem List | Problem List Stage 1 AMC measure | Yes | Milestone5
4761 | Problem List | Problem List Stage 1 AMC measure does not account for patients with uncoded problems | Yes | Milestone5
3434 | Provide Clinical Summary | Help text and Threshold value for Provide Clinical Summary stage 1 AMC measure | Yes | Milestone5
4762 | Provide Clinical Summary | Provide Clinical Summary Stage 1 AMC measure does not account visits outside reporting period | Yes | Milestone5
4763 | Provide Clinical Summary | Provide Clinical Summary Stage 1 AMC measure does not account non Face-to-Face patients | Yes | Milestone5
4764 | Provide Clinical Summary | Provide Clinical Summary Stage 1 AMC measure does not account Inpatients | Yes | Milestone5
4765 | Provide Clinical Summary | Provide Clinical Summary Stage 1 AMC measure does not account inactive visits | Yes | Milestone5
4766 | Provide Clinical Summary | Provide Clinical Summary AMC stage 1 measure. (+ve scenarios with exam on Weekdays) | Yes | Milestone5
4767 | Provide Clinical Summary | Provide Clinical Summary Stage 1 AMC measure (-ve scenario exams on Weekdays) | Yes | Milestone5
6725_1 | Provide Clinical Summary | Verification of Positive scenarios with exam on Weekends in Provide Clinical Summary AMC stage 1 measure - 96 hours & Saturday | Yes | Milestone5
6725_2 | Provide Clinical Summary | Verification of Positive scenarios with exam on Weekends in Provide Clinical Summary AMC stage 1 measure - 110 hours & Saturday | Yes | Milestone5
6725_3 | Provide Clinical Summary | Verification of Positive scenarios with exam on Weekends in Provide Clinical Summary AMC stage 1 measure - 80 hours & Sunday | Yes | Milestone5
6725_4 | Provide Clinical Summary | Verification of Positive scenarios with exam on Weekends in Provide Clinical Summary AMC stage 1 measure - 95 hours & Sunday | Yes | Milestone5
6725_5 | Provide Clinical Summary | Verification of Positive scenarios with exam on Weekends in Provide Clinical Summary AMC stage 1 measure - 85 hours & Friday | Yes | Milestone5
6725_6 | Provide Clinical Summary | Verification of Positive scenarios with exam on Weekends in Provide Clinical Summary AMC stage 1 measure - 119 hours & Friday | Yes | Milestone5
6726_1 | Provide Clinical Summary | Verification of Positive scenarios with exam on US Federal Holidays in Provide Clinical Summary AMC stage 1 measure - 80 hours | Yes | Milestone5
6726_2 | Provide Clinical Summary | Verification of Positive scenarios with exam on US Federal Holidays in Provide Clinical Summary AMC stage 1 measure - 95 hours | Yes | Milestone5
6727_1 | Provide Clinical Summary | Verification of Negative scenarios with exams on Weekends in Provide Clinical Summary Stage 1 AMC measure - on Saturday | Yes | Milestone5
6727_2 | Provide Clinical Summary | Verification of Negative scenarios with exams on Weekends in Provide Clinical Summary Stage 1 AMC measure - on Friday | Yes | Milestone5
6728 | Provide Clinical Summary | Provide Clinical Summary Stage 1 AMC measure (-ve scenario exams on US Federal Holiday) | Yes | Milestone5

## Milestone6
Milestone 6 Delivery Details
QC Test Scenario ID | Section | Title | Delivered | Actual Milestone | Acceptance Status ( by DRSYS QA) | Accepted By | Accepted Date | Comments
527 | Smoking Status | Smoking Status stage 1 AMC measure | Yes | Milestone6
3801 | Smoking Status | Help text and Requirement for Stage 1 Smoking Status AMC measure | Yes | Milestone6
4768 | Smoking Status | Smoking Status Stage 1 AMC measure does not account patients seen outside reporting period | Yes | Milestone6
4770 | Smoking Status | Smoking Status Stage 1 AMC measure does not account for non Face-to-Face patients | Yes | Milestone6
4771 | Smoking Status | Smoking Status Stage 1 AMC measure does not account or Inpatients | Yes | Milestone6
4772 | Smoking Status | Smoking Status Stage 1 AMC measure does not take into account patients with inactive visits | Yes | Milestone6
4774 | Smoking Status | Smoking Status Stage 1 AMC measure does not accounts for patients less than 13 years of age | Yes | Milestone6
4229 | Transition Summary of Care | Transition Summary of Care stage 1 AMC measure | Yes | Milestone6
4230 | Transition Summary of Care | Help text and Requirement column for Transition Summary of Care Stage 1 AMC measure | Yes | Milestone6
4775 | Transition Summary of Care | Transition Summary of Care does not account for patients having referrals outside reporting period | Yes | Milestone6
4776 | Transition Summary of Care | Transition Summary of Care does not account for non Face-to-Face patients with referrals | Yes | Milestone6
4777 | Transition Summary of Care | Transition Summary of Care does not account for Inpatients with referrals | Yes | Milestone6
4778 | Transition Summary of Care | Transition Summary of Care does not account for for inactive visits | Yes | Milestone6
2734 | Send Reminders | Send Reminders:Clicking EOE (not taking patient reminder preference into consideration) | Yes | Milestone6
3241 | Send Reminders | Send Reminders:Send button (not taking patient reminder preference into consideration) | Yes | Milestone6
3251 | Send Reminders | Send button should not be displayed when current date is not within reporting period | Yes | Milestone6
6540 | Send Reminders | Send Reminder (2014; EOE): Does not account visits outside RP (not considering reminder preference) | Yes | Milestone6
6541 | Send Reminders | SendReminder(2014;EOE):Does not account non face to face visit (not considering reminder preference) | Yes | Milestone6
6542 | Send Reminders | SendReminder(2014;EOE):Does not account Inpatient visit (not considering reminder preference) | Yes | Milestone6
6543 | Send Reminders | SendReminder(2014;EOE):Does not account Inactive visit (not considering reminder preference) | Yes | Milestone6
7680 | Patient Electronic Access | Patient Electronic Access Stage 1 AMC measure (+ve scenario only considering exam Weekdays) | Yes | Milestone6
7681 | Patient Electronic Access | Help text for and requirement column for Patient Electronic Access Stage 1 AMC measure | Yes | Milestone6
7682 | Patient Electronic Access | Patient Electronic Access Stage 1 AMC measure (-ve scenario with exams on weekdays) | Yes | Milestone6
7683 | Patient Electronic Access | Patient Electronic Access Stage 1 AMC measure does not account for visits outside reporting period | Yes | Milestone6
7684 | Patient Electronic Access | Patient Electronic Access Stage 1 does not take into account visits with 'Count for MU' unchecked | Yes | Milestone6
7685 | Patient Electronic Access | Patient Electronic Access Stage 1 measure does not take into account Inpatient visits | Yes | Milestone6
7686 | Patient Electronic Access | Patient Electronic Access Stage 1 does not consider inactive visits | Yes | Milestone6
7687_1 | Patient Electronic Access | Verification of Positive scenarios considering exams on weekends in Patient Electronic Access Stage 1 AMC measure - Saturday | Yes | Milestone6
7687_2 | Patient Electronic Access | Verification of Positive scenarios considering exams on weekends in Patient Electronic Access Stage 1 AMC measure - Sunday | Yes | Milestone6
7687_3 | Patient Electronic Access | Verification of Positive scenarios considering exams on weekends in Patient Electronic Access Stage 1 AMC measure - Saturday & Sunday | Yes | Milestone6
7687_4 | Patient Electronic Access | Verification of Positive scenarios considering exams on weekends in Patient Electronic Access Stage 1 AMC measure - Thursday | Yes | Milestone6
7688_1 | Patient Electronic Access | Verification of Positive scenario considering US Federal Holidays in Patient Electronic Access Stage 1 AMC measure - on US Federal Holiday | Yes | Milestone6
7688_2 | Patient Electronic Access | Verification of Positive scenario considering US Federal Holidays in Patient Electronic Access Stage 1 AMC measure - 2 days prior to us federal holiday | Yes | Milestone6
7689_1 | Patient Electronic Access | Verification of Negative scenarios considering exams on Weekends in Patient Electronic Access Stage 1 AMC measure - Saturday(144.5 hours) & Sunday(120.5 hours) | Yes | Milestone6
7689_2 | Patient Electronic Access | Verification of Negative scenarios considering exams on Weekends in Patient Electronic Access Stage 1 AMC measure -Saturday(145 hours) & Sunday(121 hours) | Yes | Milestone6
7689_3 | Patient Electronic Access | Verification of Negative scenarios considering exams on Weekends in Patient Electronic Access Stage 1 AMC measure - Thursday | Yes | Milestone6
7690_1 | Patient Electronic Access | Verification of Negative scenario with exams on US Federal Holidays in Patient Electronic Access Stage 1 AMC measure - on US Federal Holiday | Yes | Milestone6
7690_2 | Patient Electronic Access | Verification of Negative scenario with exams on US Federal Holidays in Patient Electronic Access Stage 1 AMC measure - 2 days prior to us federal holiday | Yes | Milestone6

## Milestone8
Milestone 8 Delivery Details
QC Test Scenario ID | Section | Title | Delivered | Actual Milestone | Acceptance Status ( by DRSYS QA) | Accepted By | Accepted Date | Comments
1123 | Allergies | To add Allergies via Non Compliance Report - Positive scenario | Yes | Milestone8
7404 | Allergies | To add Allergy for visit via Non Compliance - Negative scenario | Yes | Milestone8
7410 | Allergies | To add Allergies via Non Compliance Report - Multiple visit for patient | Yes | Milestone8
1128 | Clinical Summary (EOE) | To complete EOE via Non Compliance Report | Yes | Milestone8
7406 | Clinical Summary (EOE) | To complete EOE via Non Compliance - Multiple Visits on single day | Yes | Milestone8
7411 | Clinical Summary (EOE) | To complete EOE via Non Compliance - Multiple Visits on different day | Yes | Milestone8
7407 | Demographics | Verify visits getting disappear from Non Compliance list when all Demographics values re entered for patient | Yes | Milestone8
7408 | Demographics | To add patient demographic values via Non Compliance Report - Patient with multiple visits | Yes | Milestone8
1127 | Family History | To Add Family History Status via Non Compliance Report | Yes | Milestone8
7409 | Family History | To Add Family History Status via Non Compliance Report - Multiple visits for patient | Yes | Milestone8
955 | General | Verify that user can generate Non Compliance report for All Providers | Yes | Milestone8
956 | General | Verify that user can generate Non Compliance Report for All Sites | Yes | Milestone8
957 | General | Verify that user can generate Non Compliance Report for Inactive Visits | Yes | Milestone8
1120 | General | Verify that user can edit visit information from Non Compliance dialog | Yes | Milestone8
1612 | General | Verify that user can generate Non Compliance Report for visits with no assigned EP | Yes | Milestone8
1613 | General | Verify that user can 'Activate' Inactivated visits from Non Compliance report | Yes | Milestone8
1614 | General | Verify that user can 'Deactivate' Activated visits from Non Compliance report | Yes | Milestone8
1615 | General | Verify that user can 'Delete' Activated visits from Non Compliance report | Yes | Milestone8
1616 | General | Verify that user can generate Non Compliance Report for a single EP | Yes | Milestone8
1617 | General | Verify that user can generate Non Compliance Report for a single Site | Yes | Milestone8
1618 | General | Verify that user can generate Non Compliance Report for visits with no assigned Sites | Yes | Milestone8
4209 | General | Verify all defaults values for checkboxes and fields available in Non Compliance report page | Yes | Milestone8
4210 | General | Verify that Non Compliance report filters exams appropriately based on 'Include visits with Count for MU unset' checkbox | Yes | Milestone8
4211_1 | General | Verify that user can mark exam compliance as 'Count for MU' via Non Compliance Report - Health Status | Yes | Milestone8
4211_2 | General | Verify that user can mark exam compliance as 'Count for MU' via Non Compliance Report - Visit | Yes | Milestone8
6082 | General | Verify user can edit reason for visit and chief complaint from Non Compliance report | Yes | Milestone8
7418 | General | Verify user can generate Non Compliance Report for visits entered by specific User | Yes | Milestone8
6043 | Medication Reconciliation | Verification of Completing Med Reconciliation related Non Compliance by adding Medication | Yes | Milestone8
6044 | Medication Reconciliation | Verification Completing Med Reconciliation related Non Compliance by clicking on None Known | Yes | Milestone8
6063 | Medication Reconciliation | Verification of Completing Med Reconciliation related Non Compliance by adding a CPOE order | Yes | Milestone8
6064 | Medication Reconciliation | Verification of Completing Med Reconciliation related Non Compliance through Reconcile dialog | Yes | Milestone8
6065 | Medication Reconciliation | Verification of Med Reconciliation check box disabled when organization opts out of reconciliation | Yes | Milestone8
6067 | Medication Reconciliation | Verification of Completing Med Reconciliation related Non Compliance by adding medication for a visit with TOC | Yes | Milestone8
6070 | Medication Reconciliation | Verification of Completing Med Reconciliation related Non Compliance by clicking None Known for a visit with TOC | Yes | Milestone8
7419 | Medication Reconciliation | Verification of Completing Med Reconciliation related Non Compliance for patient having multiple visits on single day | Yes | Milestone8
1124 | Medications | To Add Medication via Non Compliance Report | Yes | Milestone8
7412 | Medications | To Add Medication via Non Compliance Report - Patient having multiple visits | Yes | Milestone8
1112 | Problems | To Add Problem via Non Compliance Report - Positive scenario | Yes | Milestone8
7413 | Problems | To Add Problem via Non Compliance Report - Negative Scenario | Yes | Milestone8
7414 | Problems | To Add Problem via Non Compliance Report - Multiple visits for patient | Yes | Milestone8
1126 | Smoking Status | To Add Smoking Status via Non Compliance Report | Yes | Milestone8
7415 | Smoking Status | To Add Smoking Status via Non Compliance Report - Patient having multiple visits | Yes | Milestone8
7416 | Vitals | To Add All Vitals via Non Compliance Report | Yes | Milestone8
7417 | Vitals | To Add Vitals via Non Compliance Report - Patient having multiple visits | Yes | Milestone8

## Milestone10
Milestone 10 Delivery Details
QC Test Scenario ID | Section | Title | Delivered | Actual Milestone | Acceptance Status ( by DRSYS QA) | Accepted By | Accepted Date | Comments
897 | Allergies | Verify that the user can add Med Allergies to an existing patient record | Yes | Milestone10
898 | Allergies | Verify that the user can update Med Allergies added to an existing patient record | Yes | Milestone10
899 | Allergies | Verify that the user can delete Med Allergies added to an existing patient | Yes | Milestone10
3557 | Allergies | Verify that the user can add Med Allergies to a new patient | Yes | Milestone10
3558 | Allergies | Verify that the user can Add None Known for allergies for a new patient | Yes | Milestone10
3588 | Family History | Verify that the user can add None Known for Family history for a new patient | Yes | Milestone10
1603 | Family History | Verify that the user can add Family history to an existing patient record | Yes | Milestone10
1604 | Family History | Verify that the user can Inactivate Family history of an existing patient record | Yes | Milestone10
2390 | Family History | Verify that the user can Activate Family history of an existing patient record | Yes | Milestone10
1605 | Family History | Verify that the user can Delete Family history of an existing patient record | Yes | Milestone10
2380 | Family History | Verify that the user can add an Uncoded Family History related to every relationship manually for an existing patient | Yes | Milestone10
2378 | Family History | Verify that the user can add an Uncoded Family History related to every relationship manually for a new patient | Yes | Milestone10
2387 | Family History | Verify that the user cannot add the same Coded/Uncoded Family History (related to same Relationship) more than once
3586 | Family History | Verify that the user can add Family History to a new patient | Yes | Milestone10
893 | Medication | Verify that the user can add Medications to an existing patient record | Yes | Milestone10
894 | Medication | Verify that the user can Activate or Inactivate Medications added to an existing patient record | Yes | Milestone10
895 | Medication | Verify that the user can Delete Medications added to an existing patient record | Yes | Milestone10
3560 | Medication | Verify that the user can Add Medication to a new patient | Yes | Milestone10
3561 | Medication | Verify that the user can Add None Known for Medication for a new patient | Yes | Milestone10
891 | Problems | Verify that the user can add problems to an existing patient | Yes | Milestone10
892 | Problems | Verify that the user can Update the already added problems of an existing patient | Yes | Milestone10
896 | Problems | Verify that the user can Delete already added problems of an existing patient | Yes | Milestone10
3392 | Problems | Verify that the user can Add ,Edit and Delete problems to a new patient | Yes | Milestone10
3576 | Problems | Verify that the user can Add None Known for problems for a new patient | Yes | Milestone10
900 | Smoking Status | Verify that the user can Add smoking status to a patient record | Yes | Milestone10
901 | Smoking Status | Verify that the user can Update smoking status added to a patient record | Yes | Milestone10
902 | Vitals | Verify that the user can Add vitals to a new patient | Yes | Milestone10
903 | Vitals | Verify that the user can Update vitals added to an existing patient record | Yes | Milestone10
889 | General | Verify that the details of an existing patient can be updated | Yes | Milestone10
1606 | Medication | Verify that selected EP is considered as the default EP for new or existing patient | Yes | Milestone10
1608 | Medication | Verify that the patient and exam can be created with no single-race or do not count for MU | Yes | Milestone10
1609 | Medication | Verify that the exam can be created with out including visiting notes | Yes | Milestone10
3573 | Medication | Verify that the MU Check is showing correctly when creating a new exam | Yes | Milestone10
3574 | Medication | Verify that the Organization settings for CPT is showing correctly when creating a new exam | Yes | Milestone10
7322 | Medication | Verify that the "Ethnicity" is spelled correctly in patient Demographics section | Yes | Milestone10

## Script Review
Test Scripts Review Status
Folder | Script Name | Reviewed ? | Latest Reviewed Date | Script Update Date
\config | config.yml | No | 2014-11-26 | 2014-12-05
| cucumber.yml | No | 2014-11-26 | 2014-12-05
\features\desktop\compliance\amc\stage1\cpoe_medication | cpoe_for_medication_orders.feature | No
| cpoe_for_medication_orders_alternate.feature | No
\features\desktop\compliance\amc\stage1\demographics | demographics.feature | No
\features\desktop\compliance\amc\stage1\erx | generate_and_transmit_erx.feature | No
\features\desktop\compliance\amc\stage1\generate_patient_list | generate_patient_list.feature | No
\features\desktop\compliance\amc\stage1\med_allergy | medication_allergy.feature | No
\features\desktop\compliance\amc\stage1\med_reconciliation | med_reconciliation.feature | No
\features\desktop\compliance\amc\stage1\medication_list | medication_list.feature | No
\features\desktop\compliance\amc\stage1\patient_education | patient_education.feature | No
\features\desktop\compliance\amc\stage1\patient_electronic_access | patient_electronic_access.feature | No
\features\desktop\compliance\amc\stage1\problem_list | problem_list.feature | No
\features\desktop\compliance\amc\stage1\provide_clinical_summary | provide_clinical_summary.feature | No
\features\desktop\compliance\amc\stage1\send_remainders | send_remainders.feature | No
\features\desktop\compliance\amc\stage1\smoking_status | smoking_status.feature | No
\features\desktop\compliance\amc\stage1\transition_summary_of_care | transition_summary_of_care.feature | No
\features\desktop\compliance\amc\stage2\cpoe | cpoe_for_laboratory_orders.feature | No | 2014-11-26 | 2014-12-05
| cpoe_for_medication_orders.feature | No | 2014-11-26 | 2014-12-05
| cpoe_for_radiology_orders.feature | No | 2014-11-26 | 2014-12-05
\features\desktop\compliance\amc\stage2\demographics | demographics.feature | No | 2014-11-26 | 2014-12-05
\features\desktop\compliance\amc\stage2\electronic_notes | record_electronic_notes.feature | No | 2014-11-26 | 2014-12-05
\features\desktop\compliance\amc\stage2\erx | generate_and_transmit_erx.feature | No | 2014-11-26 | 2014-12-05
\features\desktop\compliance\amc\stage2\family_health_history | family_health_history.feature | No | 2014-11-26 | 2014-12-05
\features\desktop\compliance\amc\stage2\generate_patient_list | generate_patient_list.feature | No | 2014-11-26 | 2014-12-05
\features\desktop\compliance\amc\stage2\lab_results | incorporate_clinical_lab_results.feature | No | 2014-11-26 | 2014-12-05
| incorporate_clinical_lab_results_hl7.feature | No
\features\desktop\compliance\amc\stage2\med_reconciliation | med_reconciliation.feature | No | 2014-11-26 | 2014-12-05
\features\desktop\compliance\amc\stage2\patient_education | patient_education.feature | No | 2014-11-26 | 2014-12-05
\features\desktop\compliance\amc\stage2\patient_electronic_access | patient_electronic_access.feature | No | 2014-11-26 | 2014-12-05
\features\desktop\compliance\amc\stage2\preventive_care | preventive_care.feature | No | 2014-11-26 | 2014-12-05
\features\desktop\compliance\amc\stage2\provide_clinical_summary | provide_clinical_summary.feature | No | 2014-11-26 | 2014-12-05
\features\desktop\compliance\amc\stage2\smoking_status | smoking_status.feature | No | 2014-11-26 | 2014-12-05
\features\desktop\compliance\amc\stage2\vital_signs | vital_signs.feature | No | 2014-11-26 | 2014-12-05
| vital_signs_blood_pressure.feature | No | 2014-11-26 | 2014-12-05
| vital_signs_hight_weight.feature | No | 2014-11-26 | 2014-12-05
\features\desktop\compliance\non_compliance\allergies | allergies.feature | No
\features\desktop\compliance\non_compliance\clinical_summary | clinical_summary.feature | No
\features\desktop\compliance\non_compliance\demographics | demographics.feature | No
\features\desktop\compliance\non_compliance\family_history | family_history.feature | No
\features\desktop\compliance\non_compliance\general | non_compliance_gereral.feature | No
\features\desktop\compliance\non_compliance\med_reconciliation | med_reconciliation.feature | No
\features\desktop\compliance\non_compliance\medications | medications.feature | No
\features\desktop\compliance\non_compliance\problems | problems.feature | No
\features\desktop\compliance\non_compliance\smoking_status | smoking_status.feature | No
\features\desktop\compliance\non_compliance\vitals | vitals.feature | No
\library\app_init | app_driver.rb | Yes | 2014-11-26 | 2014-12-05
\library\app_specific | data_file_names.rb | No | 2014-11-26 | 2014-12-05
| hl7_utils.rb | No
| holiday.rb | No
| menu_traverse.rb | Yes | 2014-11-26 | 2014-12-05
| page_utils.rb | No | 2014-11-26 | 2014-12-05
| pagination.rb | No | 2014-11-26 | 2014-12-05
\library\app_utils | HL7Sender.jar | No
\library\generic | app_logo_1.png | Yes | 2014-11-26 | 2014-12-05
| create_log.rb | Yes | 2014-11-26 | 2014-12-05
| custom_html_report.rb | No | 2014-11-26 | 2014-12-05
| datetime_library.rb | Yes | 2014-11-26 | 2014-12-05
| file_library.rb | No | 2014-11-26 | 2014-12-05
| performance_report.rb | No
| read_from_yml.rb | No | 2014-11-26 | 2014-12-05
\library\hl7_messages\templates | lab_order_with_multiple_results.txt | No
| negative_lab_order_and_result.txt | No
| not_positive_negative_numeric_lab_order_and_result.txt | No
| not_positive_negative_numeric_lab_order_and_result1.txt | No
| numeric_lab_order_and_result.txt | No
| positive_lab_order_and_result.txt | No
\object_repository\desktop | AMC_stage.rb | No | 2014-11-26 | 2014-12-05
| clinical_documents.rb | Yes | 2014-11-26 | 2014-12-05
| create_ep.rb | No | 2014-11-26 | 2014-12-05
| create_exam.rb | No | 2014-11-26 | 2014-12-05
| create_patient.rb | No | 2014-11-26 | 2014-12-05
| demographics.rb | No | 2014-11-26 | 2014-12-05
| document_note.rb | Yes | 2014-11-26 | 2014-12-05
| family_history.rb | No | 2014-11-26 | 2014-12-05
| generate_patient_list.rb | No | 2014-11-26 | 2014-12-05
| health_status.rb | No | 2014-11-26 | 2014-12-05
| lab_results.rb | No | 2014-11-26 | 2014-12-05
| login_page.rb | No | 2014-11-26 | 2014-12-05
| master_page.rb | No | 2014-11-26 | 2014-12-05
| medication_allergy.rb | No
| medication_list.rb | No | 2014-11-26 | 2014-12-05
| non_compliance_report.rb | No
| order_entry.rb | No | 2014-11-26 | 2014-12-05
| order_entry_laboratory.rb | Yes | 2014-11-26 | 2014-12-05
| order_entry_medications.rb | No | 2014-11-26 | 2014-12-05
| order_entry_radiology.rb | Yes | 2014-11-26 | 2014-12-05
| problem_list.rb | No | 2014-11-26 | 2014-12-05
| reconcile.rb | Yes | 2014-11-26 | 2014-12-05
| search_patient.rb | No | 2014-11-26 | 2014-12-05
| send_patient_remainders.rb | Yes | 2014-11-26 | 2014-12-05
| site.rb | No
| site_administration.rb | No
| transition_of_care_document.rb | No | 2014-11-26 | 2014-12-05
| users_and_groups.rb | No
| visit_notes.rb | No | 2014-11-26 | 2014-12-05
\step_definitions\desktop\compliance\amc | amc_report_page_steps.rb | No | 2014-11-26 | 2014-12-05
| numerator_report_steps.rb | No | 2014-11-26 | 2014-12-05
\step_definitions\desktop\compliance\non_compliance | non_compliance_report_steps.rb | No
\step_definitions\desktop\demographics | demographics_steps.rb | No | 2014-11-26 | 2014-12-05
\step_definitions\desktop\health_status | health_status_steps.rb | No | 2014-11-26 | 2014-12-05
\step_definitions\desktop\master_page | login_steps.rb | No | 2014-11-26 | 2014-12-05
| mu_checklist_ribbon_steps.rb | No
| page_navigation_steps.rb | No
\step_definitions\desktop\order_entry_results | hl7_messaging_steps.rb | No
| lab_results_steps.rb | No | 2014-11-26 | 2014-12-05
| order_entry_results_steps.rb | No | 2014-11-26 | 2014-12-05
\step_definitions\desktop\select_patient | exam_steps.rb | No | 2014-11-26 | 2014-12-05
| patient_steps.rb | No | 2014-11-26 | 2014-12-05
\step_definitions\desktop\setup | ep_steps.rb | No | 2014-11-26 | 2014-12-05
| med_reconciliation_steps.rb | Yes | 2014-11-26 | 2014-12-05
| site_administartion_steps.rb | No
| site_steps.rb | No
\step_definitions\desktop\tasks | generate_patient_list_steps.rb | Yes | 2014-11-26 | 2014-12-05
| send_patient_remainder_page_steps.rb | Yes | 2014-11-26 | 2014-12-05
\step_definitions\desktop\visit_notes | record_electronic_notes_steps.rb | No | 2014-11-26 | 2014-12-05
\support | browser_settings.rb | No | 2014-11-26 | 2014-12-05
| env.rb | No | 2014-11-26 | 2014-12-05
| hooks.rb | No | 2014-11-26 | 2014-12-05
| html_formatter.rb | No |  | 2014-12-05
\features\mobile\clinical_data\patient_allergies | allergies.feature | No
\features\mobile\clinical_data\patient_family_history | family_history.feature | No
\features\mobile\clinical_data\patient_medications | medications.feature | No
\features\mobile\clinical_data\patient_problems | problems.feature | No
\features\mobile\clinical_data\patient_smoking_status | smoking_status.feature | No
\features\mobile\clinical_data\patient_vitals | vitals.feature | No
\features\mobile\clinical_data\patient_medications | medications.feature | No
\features\mobile\general\general_case | general.feature | No
\object_repository\mobile | clinical_data_page.rb | No
| dashboard_page.rb | No
| desktop_health_status.rb | No
| desktop_master_page.rb | No
| desktop_visit_page.rb | No
| ep_page.rb | No
| exam_page.rb | No
| master_page.rb | No
| mobile_login_page.rb | No
| patient_page.rb | No
\step_definitions\mobile | clinical_data_steps.rb | No
| ep_steps.rb | No
| exam_steps.rb | No
| master_steps.rb | No
| mobile_login_steps.rb | No
| patient_steps.rb | No